## LAUNCH MATRIX (NEW)
LAUNCH MATRIX
[6 empty] | CODE FREEZE |  | QA TESTING COMPLETE |  | Release Date (EA or GA) |  | STATUS |  | TICKETS & CUSTOMERS
Mile | Done | Model/Library | Version | Distributed | PIC | Planned | Actual | Planned | Actual | Planned | Actual | Status | Notes — why it is at risk / what is happening | OSRB Ticket | NSpect Ticket | Other Tickets / Links | EA Customers
August EA - for RFM NIM (COMPLETE)
Kumo Relational (RFM v2.0) - EA Release (Alex Porter)
|  | RFM Weights | V2 | Weights: - inside NIM only | Won't do HF (per PM) | N/A |  |  |  | N/A (released with container) |  |  |  | combined with NIM, since weights are only released inside nim | https://nspect.nvidia.com/registration/programs/22195/versions/73960
|  | RFM NIM | V2 | NIM - NGC - Build Playground | Alex | 2026-07-17 | 2026-07-17 | 2026-07-15 | 2026-07-12 | 2026-08-24 | 2026-09-10 | Complete | Alex to send Oracle instructions today | https://nvbugspro.nvidia.com/bug/6457167 | https://nspect.nvidia.com/review?id=NSPECT-B1D1-PT0E | 4 more — SDK/notebook OSRB nvbug 6470036, container NSPECT-ZP0R-U13D, AI card 3129, compliance tracker. See Tickets tab.
Foundation Model Client
|  | Client for Foundation Models | V1 (pql support for RFM v2.x only) | - GitHub - PyPI | Manush | 2026-08-11 |  | NA | NA | 2026-08-24 | 2026-09-08 | Complete | Kumo Relational Client is public All three packages are now on PyPI at 1.0.0 under Apache-2.0: • https://pypi.org/project/kumo-relational-client/ • https://pypi.org/project/kumo-relational-engine/ • https://pypi.org/project/kumo-connectors/ | https://nvbugspro.nvidia.com/bug/6470036 | https://nspect.nvidia.com/review?id=NSPECT-USU5-DBYK | https://github.com/NVIDIA/kumo-relational-client
September EA - for Kumo 3
Kumo 3 EA
|  | Kumo 3 Studio - EA only (inc UI/Temporal etc) | v3.1 - EA EA for NPCI, Santander, Paypal. | Docker Container on - NGC | Joseph | 2026-09-04 |  | NA |  | 2026-09-18 | 2026-09-16 | Complete | Effy /Fonda to respond on thread with Update.. Update Disha on developments when back. Code complete provided OSRB submitted 7-Aug, which unblocks Santander, Coinbase, Affirm and P&G. On-prem install (DGX Spark) landed 24-Jul and SaaS staging envs 31-Jul. Planned GA of 15-Aug sits before the 31-Aug Santander install, so the sequence needs fixing. Open question: restart OSRB and jump straight to 3.1? | https://nvbugspro.nvidia.com/bug/6441538 (Prev) https://nvbugspro.nvidia.com/bug/6619129 (Current) | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2 |  | Santander, NPCI, P&G, Paypal
|  | Kumo 3 SDK (for both pip install and container) | v3.1 - EA EA for NPCI, Santander, Paypal. | Private Github shared with Snowflake and EA container customers (NPCI, Santander, Paypal, etc) | Joseph | 2026-09-04 |  | NA |  | 2026-09-04 | 2026-08-14 | Complete | Code complete provided OSRB submitted 7-Aug, which unblocks Santander, Coinbase, Affirm and P&G. On-prem install (DGX Spark) landed 24-Jul and SaaS staging envs 31-Jul. Planned GA of 15-Aug sits before the 31-Aug Santander install, so the sequence needs fixing. Open question: restart OSRB and jump straight to 3.1? | https://nvbugspro.nvidia.com/bug/6441538 (Prev) https://nvbugspro.nvidia.com/bug/6619129 (Current) | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2 |  | Santander, NPCI, P&G, Paypal
|  | Kumo 3 Core + Snowflake pip install | v3.1 - EA EA for Akhil at Snowflake | PID | Haowei | 2026-09-04 |  | NA |  | 2026-09-23 |  | Complete | Hema to sync directly with Haowei EA is pending OSRB approval. EA distribution will be via PID, to snowflake NVOnline site | https://nvbugspro.nvidia.com/bug/6649311 | https://nspect.nvidia.com/registration/programs/22455/versions/76584 | export compliance: https://nvbugspro.nvidia.com/bug/6649311
SDM v1 (Ramona)
|  | "SDM" | v1 | Github | Aki | 2026-08-20 | 2026-08-31 | N/A |  | 2026-09-28 |  | On Track | Escalated -- legal blockers that Aleksandar will resolve by Sep 4. QA is owned by ourselves as this proj is "Type II open source projects (beta)" | https://nvbugspro.nvidia.com/bug/6630830 | https://nspect.nvidia.com/review?id=NSPECT-MAR9-ANXN | Repo: github.com/NVIDIA/structured-data-models
Oct - GTC Berlin GA Releases
Kumo 3 Fine Tuning - pip install / Excludes Studio or Container (Effy Fang). Note: discuss in next meeting as we'll be 1 month out
|  | Kumo 3 Source Code (for core "pip install") | v3.1 - GA | Github | Min | 2026-09-30 | 2026-10-05 | N/A |  | 2026-10-16 | 2026-10-18 | On Track | Aleksandar to discuss GA legal launch with Robin 'Decision made on 8/26 to GA Kumo3 as a monorepo. only kumo-core, kumo-diskgraph, snowflake adaptor, dbx adaptor, and sdk client are in GA scope, though other packages will be included in the monorepo by code freeze time. | https://nvbugspro.nvidia.com/bug/6648800 | https://nspect.nvidia.com/registration/programs/22455/versions/78151
|  | Kumo 3 standalone pip install | v3.1 - GA | PyPI | Min | 2026-09-30 | 2026-10-05 | N/A |  | 2026-10-16 | 2026-10-16 | On Track | only snowflake, dbx, Linux & cloud notebook with GPU and SSD are in scope for GA. no mac or windows. | same as above | same as above
|  | Kumo 3 on Snowflake ML | v3.1 - GA | As part of Snowflake Default Runtime | Haowei | 2026-09-30 | 2026-10-05 | N/A |  | 2026-10-16 | 2026-10-16 | On Track | EA delivery to snowflake is 9/23. minor code change for bug fix can happen between 9/23-9/30. | same as above | same as above
|  | Documentation / Website / Artifacts for Kumo 3 | v 1.0 GA | GTC artifacts | Aleks S | 2026-09-30 | 2026-10-16 | N/A |  | 2026-10-16 | 2026-10-17 | On Track | The website is back on track. The draft has been submitted for review and built. Target go-live: 10/21
Kumo 3 Coding Agent
|  | Kumo Agent | v 1.0 GA | Github | Adi | 2026-10-07 | 2026-10-05 | N/A |  | 2026-10-16 | 2026-10-18 | On Track | need to confirm GA scope asap. meeting on 10/5 | same as above (kumo-engine) | same as above
Kumo Relational (RFM v2.1) (Alex Porter)
|  | RFM Model Implementation | V2.1 (no kaggle + SDM base) | Internal | Vid | 2026-09-21 | 2026-09-21 | N/A |  | N/A (released with container)
|  | RFM Weights | V2.1 | Weights: - HF | Alex | 2026-09-30 | 2026-09-21 | N/A |  | 2026-09-28 | 2026-09-28 | On Track | model is registered as v1.1 in nspect. should be considered as a minor release, no architecture change, just retrained on new data | https://nvbugspro.nvidia.com/bug/6575672 | https://nspect.nvidia.com/registration/programs/22195/versions/78082
|  | RFM Weights - Databricks (removed Snowflake) | V2.1 | Weights: - Databricks - Snow | Adi | 2026-09-30 | 2026-09-21 | N/A |  | 2026-10-05 |  | N/A | Josh / Adi -- yes for DB re: completing before GTC Berlin. No for Snowflake (Snowflake only wants to focus on kumo3 for now)
|  | RFM NIM | V2.1 | NIM - NGC - Build | Alex | 2026-09-30 | 2026-09-30 | 2026-10-07 | 2026-10-15 | 2026-10-13 |  | On Track | NIM is ready and tested, just waiting on PLC to finish | https://nspect.nvidia.com/registration/programs/21898/versions/78093 | https://nspect.nvidia.com/registration/programs/21898/versions/78093
|  | RFM Training Data/Recipe | v2.1 | Github | Won't do (per PM) Will publish with 2.5 once we do not have ICL dependency
Foundation Model Client (Manush)
|  | Client for Foundation Models | Pql support for RFM & TFM | - GitHub - PyPI | Manush | 2026-09-14 |  | N/A |  | 2026-10-09 | 2026-10-19 | On Track | PQL library will be packaged inside this client release to avoid having seperate OSRBs. Repo created and in developement. OSRB, Nspect, and PLC in process. | http://nvbugs/6716314 | https://nspect.nvidia.com/registration/programs/24511 | https://jirasw.nvidia.com/browse/MVSB-41901
|  | Kumo Agent | Skills to work with sdm-client | Github | Adi | 2026-10-07 |  | N/A |  | 2026-10-09 |  | On Track | Released as part of v1 sdm-client release
TFM (Aleksander Sokolovski)
|  | TFM Model implementation | v1 | Internal | Aleks S | 2026-09-15 | 2026-09-15 |  |  | N/A (released with container) |  | On Track | The model is expected to complete training by Sep 8, finalizing its weights and architecture. SDM integration and inference optimization will then take at least one week.
|  | TFM Weights | v1 | Weights: - HF | Aleks S | 2026-09-15 | 2026-09-15 | N/A |  | 2026-09-29 |  | On Track | Model development is on track. Training for all classification and regression models is expected to finish by 8 Sep. The H200 memory bottleneck is being addressed. SDM targets GA on 28 Sep and may require SDM coordination. | https://nvbugspro.nvidia.com/bug/6681039 | https://nspect.nvidia.com/review?id=NSPECT-LMU5-4KJP | Reuse the existing NSpect rather than filing new
|  | TFM Wheel/partner packaging (Snowflake/Databricks) | v1 (Stretch) | For: - Databricks - Snow | Adi |  |  | N/A |  |  |  |  | need a new version and OSRB for the release see https://nvidia.slack.com/archives/C071HUXSSBA/p1788014861845669?thread_ts=1785876613.078319&cid=C071HUXSSBA
|  | TFM Container (NIM) | v1 | NIM - NGC - Build | Aleks S | 2026-09-15 | 2026-09-17 | 2026-09-29 | 2026-10-15 | 2026-10-13 |  | On Track | need to align with build team's release cycle to make it by GTC Berlin - last release before GTC: Canary: 10/8 Production: 10/13 | https://nvbugspro.nvidia.com/bug/6681097 | https://nspect.nvidia.com/review?id=NSPECT-I0E0-OIXC
|  | TFM Training Data/Recipe | v1 | Github | Aleks S | 2026-09-29 |  | N/A |  | TBU | Not in scope for GTC Berlin. Private repo. | On Track | Not in scope for GTC Berlin. Private repo.
|  | Documentation / Website / Artifacts for TFM |  | GTC artifacts | Aleks S | 2026-09-29 |  | N/A |  | 2026-10-13 |  | On Track | Aleksandar to sync with documentation team & with Charlotte re: new website
Timeseries - Existing Model rebranded (No Client for Foundation Models/ PQL support) (Saira Qureshi)
|  | Forecasting Weights | v1 (Existing Tesseract Model rebranded) | Weights: - HF | Aditi | 2026-09-01 | [6 empty] | available on HF Wont do Snow and DBx until v2 of model |  |  | https://huggingface.co/nvidia/nv-tesseract-forecasting
|  | Forecasting Container | v1 | NIM - NGC - Build | Aditi | 2026-09-01 | [6 empty] | The container is not being supported anymore and was last updated on June 25, 2026 under EA |  | https://nspect.nvidia.com/review?id=NSPECT-21T4-GUQT | https://catalog.ngc.nvidia.com/orgs/nim/nvidia/containers/nv-tesseract/forecasting-1.0.1
|  | Forecasting Training Data/Recipe | v1 | Github | We may not do? Confirm with Matthias/Aditi/Saira | [8 empty] | https://nvbugspro.nvidia.com/bug/6010409
Anomaly - Existing Model rebranded (No Client for Foundation Models/ PQL support) (Saira Qureshi)
|  | Anomaly Weights | v1 (Existing Tesseract Model rebranded) | Weights: - HF | Aditi | 2026-09-01 | [6 empty] | available on HF |  |  | https://huggingface.co/nvidia/nv-tesseract-ad-diffusion
|  | Anomaly | v1 | NIM - NGC - Build | Aditi | 2026-09-01 | [6 empty] | The container is not being supported anymore and was last updated on June 25, 2026 under EA | https://nvbugspro.nvidia.com/bug/5672723 | https://nspect.nvidia.com/review?id=NSPECT-POGC-RJ93 | https://catalog.ngc.nvidia.com/orgs/nim/nvidia/containers/nv-tesseract/ad-diffusion-1.1.0
|  | Anomaly Training Data/Recipe | v1 | Github | We may not do? Confirm with Matthias/Aditi/Saira | 2026-09-01
December
Kumo 3 Fine Tuning - Container with Kumo 3 Studio
|  | Kumo 3 Studio - GA (inc UI/Temporal etc) | v3.1 - GA | Docker Container on - NGC | Joseph | 2026-09-30 |  | 2026-10-14 |  | 2026-10-16 |  | On Track | Code complete provided OSRB submitted 7-Aug, which unblocks Santander, Coinbase, Affirm and P&G. On-prem install (DGX Spark) landed 24-Jul and SaaS staging envs 31-Jul. Planned GA of 15-Aug sits before the 31-Aug Santander install, so the sequence needs fixing. Open question: restart OSRB and jump straight to 3.1? | https://nvbugspro.nvidia.com/bug/6441538 (Prev) https://nvbugspro.nvidia.com/bug/6619129 (Current) | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2 |  | Santander, NPCI, P&G, Paypal
Kumo 3 Fine Tuning - pip install for Dbx / Cloudera
|  | Kumo 3 on DBx MLFlow | v3.1 - GA | pip install for DBx ML runtime | Haowei | 2026-09-18 |  | N/A |  | 2026-09-23 |  | On Track | EA is blocked at PLR - legal PIC comment says we need both osrb and export compliance ticket to be approved. EA distribution is planned via NGC, resource created and wheel uploaded. need to figure out how to set up EULA next. | https://nvbugspro.nvidia.com/bug/6649311 | https://nspect.nvidia.com/registration/programs/22455/versions/76584 | export compliance: https://nvbugspro.nvidia.com/bug/6649311
|  | Kumo 3 on Cloudera | v3.1 - GA | pip install for Cloudera ML platform | Haowei | 2026-09-18 |  | N/A |  | 2026-09-23 |  | On Track | EA is blocked at PLR - legal PIC comment says we need both osrb and export compliance ticket to be approved. EA distribution is planned via NGC, resource created and wheel uploaded. need to figure out how to set up EULA next. | https://nvbugspro.nvidia.com/bug/6649311 | https://nspect.nvidia.com/registration/programs/22455/versions/76584 | export compliance: https://nvbugspro.nvidia.com/bug/6649311
PQL as standalone repo
|  | OpenSourcing PQL as standalone sub repo (for discussion) | v1 | - GitHub | Jana / Manush | 2026-12-25 |  | N/A |  | 2027-01-22 |  | On Track | PQL will be a standalone library that will be imported into client Scope to inlcude select Pql enhancements for time windows
Agents
|  | DataScience Skills for NLP Agents | v1 (required for ServiceNow & Oracle) | GitHub | Myunghwan | 2026-10-13 |  | 2026-10-13 |  | 2026-10-16 |  |  | Scope includes: - text2DAG - text2SchemaGraph (table selection and kumo schema graph formulation) - ambiquity resolver - OSI, OSSIE, GSF Semantic Models integration (via SDK) - text2pql - benchmarks |  |  | POR
Fraud Blue Print v2
|  | Fraud Blue Print v2 | v2 (using a Temporal Graph Transformer + Viz interface) May need sooner for ServiceNow? | GitHib | Joe E
January
Kumo Relational (RFM v2.5)
|  | RFM Model Implementation | V2.5 (No Tab-ICL) | Internal | Matthias | 2026-12-18 |  |  |  | N/A (released with container)
|  | RFM Weights | V2.5 | Weights: - HF | Adi | 2026-12-25 |  | N/A |  | 2027-01-22 |  | On Track
|  | RFM Weights (Snowflake/Databricks) | V2.5 | Weights: - Databricks - Snow | Adi | 2027-01-01 |  | N/A |  | 2027-01-29 |  | On Track | Estimate 1 week after publish to HF
|  | RFM Container | V2.5 | NIM - NGC - Build | Alex | 2026-12-25 |  | 2027-01-07 |  | 2027-01-22 |  | Not Started
|  | RFM Training Data/Recipe | v2.5 | Github | Matthias | 2026-12-25 |  | N/A |  | 2027-01-22 |  | On Track
Foundation Model Client
|  | Client for Foundation Models | V2/3 (Pql support for Forecasting, Anomaly Models) | - GitHub - PyPI | Jana | 2026-12-25 |  | N/A |  | 2027-01-22 |  |  | Client without PQL library importing the below
SDM v2
|  | "SDM" | v2 | Github / PyPi | Aki/Ramona/Matthias | 2026-10-06 | 2026-10-06 | N/A |  | 2026-10-14 | 2026-10-14 | On Track | Fast-follow after SDM v0.1.0 to include Kumo Tabular
|  | "SDM" | v3 | Github / PyPi | Aki/Ramona/Matthias | 2026-10-28 |  | N/A |  | 2026-11-02 |  | On Track | Training code release, Time Series Release
|  | "SDM" | v4 | Github / PyPi | Aki/Ramona/Matthias | 2026-11-25 |  | N/A |  | 2026-12-01 |  | On Track | Inference Optimizations, others
Kumo 3.5 core
|  | Kumo 3.5 core | V3.5 (includes train & inference explainability, BYO PyG model architecture cuVS for RecSys | - GitHub - PyPI - Snowflake ML, DBx, Cloudera upgrade | Joseph | 2026-12-25 |  | 2027-01-07 |  | 0 |  | Not Started
February
Forecasting - New Model competivive with TimesFM-3 + full PQL & based on SDM (Saira Qureshi)
|  | Forecasting Model | v2 | Internal (will expand into additional rows once model lands) | Aditi | [7 empty] | available on HF Wont do Snow and DBx until v2 of model |  |  | https://huggingface.co/nvidia/nv-tesseract-forecasting
March or Beyond +++
TLP
|  | Tabular Language Predictor (TLPs) | v1 | Internal (will expand into additional rows once model lands) | Vid | [7 empty] | available on HF Wont do Snow and DBx until v2 of model |  |  | https://huggingface.co/nvidia/nv-tesseract-forecasting
Blue New Blue Prints
|  | RecSys Blue Print (based on Walmart lessoms) | v1 | Internal (will expand into additional rows once model lands) | Vid | [7 empty] | available on HF Wont do Snow and DBx until v2 of model |  |  | https://huggingface.co/nvidia/nv-tesseract-forecasting
|  | Predictive Maintenance Blue Print | v1 ( (Using Anomaly foundation model or Fine Tuned architecture supported by Kumo Core 3.5) | Internal (will expand into additional rows once model lands) | Josh | [7 empty] | available on HF Wont do Snow and DBx until v2 of model |  |  | https://huggingface.co/nvidia/nv-tesseract-forecasting
Anomaly - New Model competitive on TSB-AD benchmark + full PQL & based on SDM (Saira Qureshi)
|  | Anomaly Model | v2 | Internal (will expand into additional rows once model lands) | Aditi | [7 empty] | available on HF |  |  | https://huggingface.co/nvidia/nv-tesseract-ad-diffusion
Formulas:
Release Date (EA or GA) = [Release Date (EA or GA), row above]+7
Release Date (EA or GA) = [Release Date (EA or GA), row above]
CODE FREEZE = [CODE FREEZE, row above]
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Joseph Oliveira I thought the contsainer version was postponed until after the pip install and GTC. Can you update FYI @Said Aram @Effy Fang Reply: The containers and pip install share the same kumo-core engine. Beyond the OSRB/License(s) - there is no other additional work required + we are still targeting EA for NPCI, Santander, Paypal. Reply: @Joseph Oliveira I am a tad still unclear. The container contains way more than just "Kumo core" It contains temporal, the UI, StateDB, queues, Jana's Auth and groups stuff etc etc .. a much larger code base to test If core is not code complete until Wed 30th (and by the way that scope excludes things like explainability which the UI assumes .. wont the UI be tots broken? So When is EA go date and is there a seperate OSRB ticket? Reply: @Joseph Oliveira @Effy Fang I split out EA for Kumo 3 Studio container and GA The GA line is row 47 (or thereabouts) below If the EA container is not happening we can delete this row If date is wrong let me know I dont want to add this to the Oct deliverables as October is already massive and this is not part of GTC scope -- its either September or after October (GTC) FYI @Said Aram @Hema Raghavan Reply: New OSRB ticket: https://nvbugspro.nvidia.com/bug/6619129 Reply: OSRB ticket is current blocked by DGPTT ticket: https://jirasw.nvidia.com/browse/DGPTT-5740 Reply: Target EA depends on OSRB approval and publishing containers to NGC. Given there is no SLA provided here, my best estimate is unhelpful. I can provide daily updates instead. Reply: @Joseph Oliveira can you add this new ticket to the Tickets for GTC tab please. Or confirm that I have added it correctly
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Joseph Oliveira I thought the contsainer version was postponed until after the pip install and GTC. Can you update FYI @Said Aram @Effy Fang Reply: The containers and pip install share the same kumo-core engine. Beyond the OSRB/License(s) - there is no other additional work required + we are still targeting EA for NPCI, Santander, Paypal. Reply: @Joseph Oliveira I am a tad still unclear. The container contains way more than just "Kumo core" It contains temporal, the UI, StateDB, queues, Jana's Auth and groups stuff etc etc .. a much larger code base to test If core is not code complete until Wed 30th (and by the way that scope excludes things like explainability which the UI assumes .. wont the UI be tots broken? So When is EA go date and is there a seperate OSRB ticket? Reply: @Joseph Oliveira @Effy Fang I split out EA for Kumo 3 Studio container and GA The GA line is row 47 (or thereabouts) below If the EA container is not happening we can delete this row If date is wrong let me know I dont want to add this to the Oct deliverables as October is already massive and this is not part of GTC scope -- its either September or after October (GTC) FYI @Said Aram @Hema Raghavan Reply: New OSRB ticket: https://nvbugspro.nvidia.com/bug/6619129 Reply: OSRB ticket is current blocked by DGPTT ticket: https://jirasw.nvidia.com/browse/DGPTT-5740 Reply: Target EA depends on OSRB approval and publishing containers to NGC. Given there is no SLA provided here, my best estimate is unhelpful. I can provide daily updates instead.
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Joseph Oliveira I thought the contsainer version was postponed until after the pip install and GTC. Can you update FYI @Said Aram @Effy Fang Reply: The containers and pip install share the same kumo-core engine. Beyond the OSRB/License(s) - there is no other additional work required + we are still targeting EA for NPCI, Santander, Paypal. Reply: @Joseph Oliveira I am a tad still unclear. The container contains way more than just "Kumo core" It contains temporal, the UI, StateDB, queues, Jana's Auth and groups stuff etc etc .. a much larger code base to test If core is not code complete until Wed 30th (and by the way that scope excludes things like explainability which the UI assumes .. wont the UI be tots broken? So When is EA go date and is there a seperate OSRB ticket? Reply: @Joseph Oliveira @Effy Fang I split out EA for Kumo 3 Studio container and GA The GA line is row 47 (or thereabouts) below If the EA container is not happening we can delete this row If date is wrong let me know I dont want to add this to the Oct deliverables as October is already massive and this is not part of GTC scope -- its either September or after October (GTC) FYI @Said Aram @Hema Raghavan Reply: New OSRB ticket: https://nvbugspro.nvidia.com/bug/6619129 Reply: OSRB ticket is current blocked by DGPTT ticket: https://jirasw.nvidia.com/browse/DGPTT-5740 Reply: Target EA depends on OSRB approval and publishing containers to NGC. Given there is no SLA provided here, my best estimate is unhelpful. I can provide daily updates instead.
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: see susan's message in #ext-snowflake-nvidia. there's no ETA from sf side
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New row @Aleksandar Sokolovski (cw) to PIC and update Reply: done
Note on F28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New row @Aleksandar Sokolovski (cw) to PIC and update Reply: done
Note on N44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Josh Przybylko and @Matthias Fey pls discuss.
Note on F45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New row - @Aleksandar Sokolovski (cw) to update Reply: done
Note on G57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Joseph Oliveira I thought the contsainer version was postponed until after the pip install and GTC. Can you update FYI @Said Aram @Effy Fang Reply: The containers and pip install share the same kumo-core engine. Beyond the OSRB/License(s) - there is no other additional work required + we are still targeting EA for NPCI, Santander, Paypal. Reply: @Joseph Oliveira I am a tad still unclear. The container contains way more than just "Kumo core" It contains temporal, the UI, StateDB, queues, Jana's Auth and groups stuff etc etc .. a much larger code base to test If core is not code complete until Wed 30th (and by the way that scope excludes things like explainability which the UI assumes .. wont the UI be tots broken? So When is EA go date and is there a seperate OSRB ticket?
Note on K57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joseph Oliveira what dates in December makes sense This date looks wrong for the GA container including Studio (the UI) Reply: December 8th gives us ~5 weeks, accounting for holidays, from GTC to make any refinements to the UI.

## Launch until 2026 EOY
Release NAME | ETA | Status | PIC | Notes | LINKS
Kumo Relational NIM v1.0​ | / | Released
Kumo Relational Client v1.0​ | / | Released
Structured Data Model Library 0.1 on Github​ | / | Released
Structured Data Model Client v1.0​ | / | Released
Kumo Relational Model v1.1 Weights on Hugging Face​ | / | Released
Kumo Tabular Model v1.0 Weights on Hugging Face​ | / | Released
Structured Data Model Library v0.2​ | / | Released
Structured Data Model Client v1.0 ​ | / | Released
Kumo 3 \ Kumo Engine v1.0.0 ​ | / | Released
Rebranding for Kumo Anomaly 1.0. and Kumo Forecast 1.2​ | / | Released
* Kumo Relational v1.1​ | 10/22 2026 | In Progress |  | OSRB final step before Release
* Kumo Tabular v.10​ | 10/22 2026 | In Progress |  | OSRB final step before Release
Kumo Agent v1.0
* Structured Data Model Library 0.3​ | end of 10 - 26 | In Progress |  | OSRB under review
* TFM Training Data/Recipe | end of 10 - 26 start of 11 - 26 | Not Started |  | Release Process not Started Yet
Kumo-TS v1.0.1 (minor release) | early November | Not Started |  | Release Process not Started Yet;
NIM for Kumo Anomaly via SDM | mid November | Not Started |  | Release Process not Started Yet
NIM for Kumo Forecast via SDM | mid November | Not Started |  | Release Process not Started Yet

## Tickets for GTC
Stream |  | NSPECT ticket | Nspect Status | OSRB | DGPTT (if applicable) | OSRB staus | Date for GA
NIM v1 - RFM | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-ZP0R-U13D |  | https://nvbugspro.nvidia.com/bug/6457167 |  | done
RFM Client | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-USU5-DBYK |  | https://nvbugspro.nvidia.com/bug/6470036 |  | done
RFM v2 model/weights | NSPECT+OSRB (OSRB shared with container) | https://nspect.nvidia.com/review?id=NSPECT-B1D1-PT0E |  |  |  | done (same as NIM v1)
NIM v2 (contains RFM v2.1 and SDM base) | NSPECT + OSRB | https://nspect.nvidia.com/registration/programs/21898/versions/78093 | new version registered in rfm container program
RFM v2.1 Weights for HF/DBx | NSPECT + OSRB | https://nspect.nvidia.com/registration/programs/22195/versions/78082 | new version registered in rfm model program | https://nvbugspro.nvidia.com/bug/6575672 | https://jirasw.nvidia.com/browse/DGPTT-5804
NIM v1TFM | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-I0E0-OIXC | program created, version registered. no PLC or PLR yet | https://nvbugspro.nvidia.com/bug/6681097 | https://jirasw.nvidia.com/browse/DGPTT-5805 | new ticket, not fully filled out
TFM Weights for HF/DBx | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-LMU5-4KJP | program created, version registered. no PLC or PLR yet | https://nvbugspro.nvidia.com/bug/6681039 | https://jirasw.nvidia.com/browse/DGPTT-5806 | new ticket, not fully filled out, asked Jingang for details.
SDM | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-MAR9-ANXN | PLC initiated | https://nvbugspro.nvidia.com/bug/6630830 |  | in progress |  | Must work with RFM & TFM
SDM Client (replaces RFM client) - will include PQL here | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-3LSM-ZJXM | PLC, OSRB, Nspect initiated | https://nvbugspro.nvidia.com/bug/6716314 |  | in progress
Kevin's latest comment says we need export compliance and osrb bugs to be approved...
Kumo 3 container EA | NSPECT
Kumo 3 SDK EA | NSPECT
Kumo 3 pip install EA | NSPECT only | https://nspect.nvidia.com/registration/programs/22455/versions | blocked at PLR: https://nspect.nvidia.com/actions/compliance/legal/software/1774 | https://nvbugspro.nvidia.com/bug/6649311 |  | not started. do we really need this to be approved for EA?
Kumo 3 pip install (includes Snowflake) | NSPECT + OSRB | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2 | this is the original kumo3 program. can we use it? | https://nvbugspro.nvidia.com/bug/6648800 |  | not started
Kumo RFM + Kumo TFM Benchmarks | OSRB
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kevin's latest comment on PLR says we need OSRB approval too...

## Links to Core Assets
Core Assets Reference
Last updated: 28/09/2026
General Assets in One Drive | Link
Kumo official Sharepoint/One Drive Repository | https://nvidia.sharepoint.com/sites/Kumo
Kumo official Sharepoint/One Drive Repository All Documents | https://nvidia.sharepoint.com/sites/Kumo/Shared%20Documents/Forms/AllItems.aspx
Active Generic First Call Decks and Slides | Description |  |  | Sensitivity | Link
Kumo DevRel Marketing Official First Call Deck |  | Structured Data Processing Master Deck.pptx
Kumo DevRel Marketing Extended Deck |  | [NOT LIVE] NVIDIA Kumo Customer Deck Working Deck.pptx
Kumo General First Call Deck (Josh extended version)
Kumo Tech Deep Dive (Josh extended version) |  | Kumo_Technical Introduction_Oct6_JP
Kumo for Fraud Pitch Deck | Draft work in progress. Disha and Aser refining | NVIDIA_KUMO_Intro_Fraud_Sept22.pptx |  | Not sensitve
Kumo for Recommendations and eCommerce | [6 empty] | Catalogue clean up, recommendations/personalization
Kumo for Manufacturing and Supply Chain (with Tesseract)
Kumo for Agents and Text 2 Prediction
Kumo cuGraph for Large Scale Graph Analytics
General Library of Many Slides |  | Kumo_Extended_Slide_Library.pptx
Recently Decomissioned First Call Deck
Jun - Sept First Call Deck |  |  |  | Not sensitve | NVIDIA_KUMO_Intro_0616.pptx
Specific Presentation (may slides will overlap with the above) | Date Presented | Presented by | Presented to | Sensitivity | Link
AutoML conference tech deep dive | 28 Sept, 2026 | Jure | Conference | Public | Kumo SDGM Relational Tabular - keynote AutoML - Sep 2026.pptx
Dwight All Hands Septembet 26 | 26 Sept, 2026 | Jure | Dwight Eng | Internal | NVIDIA_KUMO_Dwight_allhands_sep26-FINAL.pptx
Kumo Dwight Team + Roadmap June 26 | 26 June, 2026 | Vanja/Jure | Dwight version | Internal | NVIDIA_KUMO_Dwight_team_jun26.pptx
JHH version of Dwight Team Roadmap deck | 29 June, 2026 | Vanja/Jure | JHH version | Internal | Frontier Structured Data and Graph Models_070226_vF.pptx
Kumo Partnership and Ecosystem Engagment Strategy | September | Vanja | Justin et al | Internal | Kumo Ecosystem Map + LHAs.pptx
Kumo PQuery Deep Dive | Not a marketing deck -- but reference |  |  |  | Kumo Model by Predictive Tasks and PQuery.pptx
Kumo + Agents a Vision (Internal) | June | Josh | Agents PMs | Internal | NVIDIA_KUMO_Agents_Intro_Jun10
Timeseries workship with Manufacturing and Supply Chain use cases | Aug | Cedric / Josh on use cases |  | Internal | Tesseract Time Series Workshop - Foundation Model Research.pptx
Ben/Roman's Transaction Foundation Model roadmap |  |  |  |  | Slides on Transaction Foundation Model roadmap
Disha's Intese deck with Model Options |  |  |  |  | nvidia_intesa_010012026.pptx
Enablement material | Date Presented | Presented by | Presented to | Sensitivity | Link
FSI SA enablement deck | 15 Oct, 2026 | Disha | FSI SAs | Internal | https://nvidia.sharepoint.com/:p:/r/sites/Kumo/_layouts/15/Doc.aspx?sourcedoc=%7BD9046AC3-8AFE-4E6B-96D2-BBE11AD75771%7D&file=NVIDIA%20Kumo%20Enablement%20Deck.pptx&action=edit&mobileredirect=true&previoussessionid=17cd4ed9-ecf9-3212-6356-25329a91f47d
SAE tech Transfer deck |  | Disha |  | Internal
Video Assets | Time |  |  | Sensitivity | Link
Kumo RFM Prediction Agent (Josh Version) 2mins | ~2min |  |  |  | KumoRFM Prediction Agent_VoiceOver_Jan17.mp4
Kumo RFM Prediction Agent (Blaj Version) | ~40 second |  |  |  | kumormf-Text2Pql_Short.mp4
Kumo RFM on Snowflake Intelligence (Josh Version) |  |  |  |  | si-sales-query.mp4
Tesseract Predictive Maintenance Demo - 7 min |  |  |  |  | NV-Tesseract Predictive Maintenance Blueprint Demo-20260904_114014-Meeting Recording.mp4
RecSys Online Serving (Door Dash like) demo |  |  |  |  | Online ServingRecSys_vFinal.mp4
Snowflake ML Integration Demo |  |  |  |  | Kumo3inSnowML_Demo_Aug3.mp4
Fraud demo - old now |  |  |  |  | Fraud_Demo_Josh Voice Over.mov
Kumo Documentation Links |  |  |  | Sensitivity | Link
Kumo Main doc | https://docs.nvidia.com/sdgm/about-nvidia-kumo/overview
Kumo Relational on docs.api | docs.api.nvidia |  |  |  | https://docs.api.nvidia.com/nim/reference/nvidia-kumo-relational
Kum-Engine Docs | https://docs.nvidia.com/sdgm/kumo-engine/get-started-with-kumo-engine/overview |  |  |  | https://docs.nvidia.com/sdgm/platform-introduction
Kumo Structured Data Model Docs | nvidia.github.io |  |  |  | https://nvidia.github.io/structured-data-models/overview.html
Kumo docs staging | https://nvidia-staging-sdgm.docs.buildwithfern.com/sdgm/about-nvidia-kumo/overview |  |  |  | https://nvidia-staging-sdgm.docs.buildwithfern.com/sdgm
SDGM Ops meetings |  |  |  | Sensitivity | Link
Link to Ops meetings. |  |  |  | Internal | Engineering Operations
Repo / Github Links / Build / Hugging Face / etc | Type | Public/Private/PrivateEA | Link
Foundation Model Libraries
Structured Data Models Repo | Git | Public | https://github.com/NVIDIA/structured-data-models
Structured Data Models on PyPI | PyPI | Public | Coming soon
Sructured Data Model Client | Git | Public | https://gitlab-master.nvidia.com/kumo-tfm-nims/sdm-client
Sructured Data Model Client | PyPI | Public | Coming soon
Kumo Tabular
Hugging Face | Weights | Public | https://huggingface.co/nvidia/Kumo-Tabular
NIM on NGC | Container | Public | Coming soon
Build & Playground | Build | Public | Coming soon
Repo (Training Data + Recipe + Example Notebooks) | Git | Internal | Coming soon
Kumo Relational
Hugging Face | Weights | Public | https://huggingface.co/nvidia/Kumo-Relational
NIM on NGC | Container | Public | nvcr.io/nim/nvidia/kumo-relational:1.0.0
Build & Playground | Build | Public | https://build.nvidia.com/nvidia/kumo-relational
Repo (Training Data + Recipe + Example Notebooks) | Git | Internal | Coming soon
Kumo Forecast (nvTesseract Forecast)
Hugging Face | Weights | Public | https://huggingface.co/nvidia/nv-tesseract-forecasting
NIM on NGC | Container | Public | Coming soon
Build & Playground | Build | Public | Coming soon
Kumo Forecast Repo | Git | Internal | https://github.com/NVIDIA/Kumo-TS |  |  | https://github.com/NVIDIA/Kumo-TS/tree/main/Kumo-Forecast
Kumo Forecast (nvTesseract Diffusion)
Hugging Face | Weights | Public | https://huggingface.co/nvidia/nv-tesseract-ad-diffusion
NIM on NGC | Container | Public | Coming soon
Build & Playground | Build | Public | Coming soon
Kumo Anomaly Repo | Git | Internal | https://github.com/NVIDIA/Kumo-TS |  |  | https://github.com/NVIDIA/Kumo-TS/tree/main/Kumo-Anomaly
Kumo-Engine (Fine tuning RDL platform)
Kumo 3 | Git | Internal | https://github.com/kumo-ai
Kumo 3 Client | Git | Internal | Coming soon
Kumo 3 on PyPI | PyPI | Internal | Coming soon
Kumo 3 NIM on NGC | Container | Private | Coming soon
Centralized Benchmark Resources |  |  | Link
Allens Leaderboard for Benchmarks on Fraud and RelBench Tasks |  |  | https://rfm-bench-978aa6.gitlab-master-pages.nvidia.com/
Product Marketing Assets |  | Sensitivity | Link
Kumo Messaging Doc |  | Internal | https://docs.google.com/document/d/1inWuFEixidPaqA7xxhafn1Ehc3TL_O2E3jnG7e3GNtI/edit?tab=t.xjsvpxqueo2u#heading=h.stpcgzr927y2
Kumo TFM Launch Blog Post |  | Internal
GTC Berlin Slide Deck |  | Internal
Actve Spec Docs |  | Sensitivity | Link
Kumo-Timeseries in SDM-Client |  | Internal | https://docs.google.com/document/d/1i-gVWzmgUTEBJ7yXjni4rt6FuC8MKfmdZlOwwgHw7Gs/edit?tab=t.0#heading=h.c0ks8judyiw6
Kumo Coding agent |  | Internal | https://nvidia.sharepoint.com/:w:/r/sites/Kumo/_layouts/15/Doc.aspx?sourcedoc=%7B55BAB10D-B5EB-4ED4-9181-303E88F182BD%7D&file=Kumo_Coding_Agent_GA_Spec_draft.docx
Feature Gen Gaps (very important) | Manush / MK | Internal | https://docs.google.com/document/d/1Q-rRvoxd6eeWpHGR4Cql8C64VhLQFoaMnW7IHla-N6U/edit?tab=t.0#heading=h.m8hiv9a42m4y

## High Level Roadmap
Kumo-Engine
| # | Item | Status | JIRA Init | Core requirements | Success Criteria | Open Questions
| 0 | Clean up of Kumo-Engine on Snowflake / Databricks pip installs + start Cloudera | In-process
| 1 | Kumo-Engine support for training/inference of sequence models (Phase 1) | Gathering |  | Training/Post-Training/Inference of existing Nvidia Transaction fraud v2 model (based on pragma) | All TransactionFM engagements move to Kumo-Engine for Training/Inference | Megatron is the alternative platfform. Can we re-use code from megatron? How will we be different?
Includes single node, Multi-GPU based training & post tuning
Scale (upcoming engagments - Ben/Roman providing details)
Batch Inference only for MVP (lets debate if we can bring into scope)
Out of scope: Novel new relational + Transaction sequence models (this comes in phase 2)
Out of scope: Online serving for Transaction Fraud model (phase 2)
Out of scope: Explainability (not yet supported in currently blue print - discuss reqs with Ben)
Out of scope: Kumo Studio for MV (may come in phase 2)
| 2 | Kumo-Engine bring your own GNN/GT/Sequence model | Gathering |  | Make it easy for users to implement their own (GNN/GT/Sequence) model architecture | Can adoption pod implement one of the architectures described by Ho, Karami & Armanfard, "Graph Anomaly Detection in Time Series: A Survey," IEEE TPAMI, 2025
Including making it simple to add a PR to make the model available others
Including hooks to expose explainability features
Including hooks to implement custom graph samples required for novel architectures
Consider breaking models into its own submodule as opposed to baked into core for easier exstensibility
| 3 | Relax strict relationship rules on Kumo graph | Gathering |  | Relax strict PK/FK rules | Reduce workarounds / feature engineering reported by adoption teams | See dependency with agents workstream: https://docs.google.com/document/d/1Q-rRvoxd6eeWpHGR4Cql8C64VhLQFoaMnW7IHla-N6U/edit?tab=t.0
Enable relationships within the same table (e.g., asset hiarachy)
Enable relationships between non PK/FK fields
Match on calc fields (extension of composite keys)
| 4 | Support feature importance for batch inference use cases (as opt in) | Deprioritize? |  | Global gradient scores, subgraph, column analysis supported and exportable (not just on scratch) | Snowflake and Databricks customers provide positibe
Add support for feature/subgraph explainer for batch inference at scale (new feature)
Supported both by pip install and Studio versions
Tech debt addressed (https://github.com/kumo-ai/kumo/pull/31295, /kumo/pull/31289)
Out of scope: feature importance for online use cases
| 6 | Bring training of RFM/TFM/Timeseries foundation models to Kumo 3 | Gathering |  | Ability to train from scratch Kumo Relational 2.5 | Training recipes that will be launched later this year should be based on Kumo-engine | What is the stack we use for training RFM/TFM? This should not be in SDM repo? Causing too much confusion
Ability to train from scratch Kumo Tabular
Out of scope: Sythetic data generators can be input to Kumo-engine and can live in SDM or elsewhere
| 5 | Bring Graph Engine to In-Context Foundation models for high batch use cases | Gathering |  | Used to scale large scale inference jobs where push down sampling not practical & support online serving |  | Do we believe that In-context models will start outperforming task specific Kumo 3 models?
| 7 | RecSys - improve scalability (hold) | Deprioritize? |  | Explore options to scale Recommender System models. Current limitations on RHS embeddings. | Sequence models are showing promise. Do we want to invest in LHS/RHS graph approach? | Can we use cuVec? Do we need in memory? Explore how turbopuffer and disk optimized algos work
| 8 | Scale disk graph beyond a single node or separate GPU vs NVMe nodes | Gathering |  | Current disk graph is limited by NVMe size. | Dissagregate GPU compute from local storage (scale beyond 1+Tb & improve GPU utilization)
Explore distributed NVMe options, Hybrid NVMe + ScyllaDB/BigTable/Cass OR + EBS io2 Block Express, etc
Explore new graph partitioning logic and data structure optimizations
Or separate nodes that has NVMe from GPU node
| 9 | Online serving architecture for Graph Fraud and Recys | Deprioritize? (focus on sequence models) |  | Expect inference data to arrive via Kafka or Kinesis. Predictions to be emitted back to Kafka/Kinesis |  | Do we still want to consider the distillation approach?
Expect sub second latency requirements
Architecture may include XGBoost as live endpoint,
or appendable "llive feature" graph store for use with a RFM or a task specific model
| 10 | Bring RecSys Sequence Models to Kumo 3 for online and high scale use cases |  |  | See https://github.com/NVIDIA/recsys-examples/tree/main/examples/hstu
Benchmarking
| # | Item | Status | JIRA Init | Core requirements | Success Criteria | Open Questions
| 1 | Create centralized benchmark repository | Gathering |  | Includes benchmarks for foundation models, including tesseract models, and fine tuned models | PM knows where to look for benchmark assets. PM knows what benchmarks are planned and what our gaps are | Can we expand on: https://rfm-bench-978aa6.gitlab-master-pages.nvidia.com/
Includes benchmark arenas
Inclused non arena datasets for Industry specific use cases:
Fraud
RecSys
Predictive Maintenance
Inventory Forcasting
Includes benchmarks for agent skills (how well does the agent formulate the task)
Includes not just model performance but scale limits & prediction latency (can we use for online serving)
SDM
| # | Item | Status | JIRA Init | Core requirements | Success Criteria | Open Questions
|  | Add suppport SDM support for Tesseract models | In-progress? |  | PM recommends we do not create a competitor to Kumo-Engine.
Keep SDM simple as an inference and acceleration layer (e.g., vLLM for structured data modeks).
Can we incorporate training/post training into kumo-engine?
In-context Foundation models
|  | Release RFM 2.5 ( |  |  | rdblearn
Open questions - can we consolidate the number of models -- we have too many
Can Kumo Relational and Kumo Tabular be combined in future?
| 5' | Accelerate Inference of Kumo Tabular

## Kumo 3 Pip Sprint
Kumo 3 pip launch timeline
Colored week cell = active duration • White = inactive • ◆ hard date • ⚠ unresolved risk
Team | PIC | Workstream | Aug 28–30 (partial) | Aug 31–Sep 6 | Sep 7–13 | Sep 14–20 | Sep 21–27 | Sep 28–Oct 4 | Oct 5–11 | Oct 12–18 | Oct 19–22 (GA week)
SHARED | Min Joseph Effy | Launch gates and Platform qualification |  | ◆ Essentials, Snowflake EA, and pip distribution code complete Qualify Snowflake EA | ◆ Platform code complete | ◆ Snowflake EA freeze Run cross-environment qualification | ◆ Snowflake EA release ◆ Benchmarking complete | ◆ Release quality complete ◆ Kumo 3.1 code freeze |  | Close release blockers | ◆ Kumo 3 pip GA
TEAM 1 Engineering | Min | Snowflake EA delivery |  | Complete Snowflake EA | Close acceptance gaps | ◆ Freeze Snowflake EA | ◆ Release Snowflake EA
| Min | Core hardening & testing | Fix critical defects and align tests | Harden essentials and core | Complete core hardening |  | Run final regression | ◆ Complete release verification
| Min | GA engineering readiness | Scope OSS cleanup | Complete readiness plan |  | Execute monorepo and environment work | Complete platform engineering | ◆ Freeze release candidate
TEAM 2 Launch readiness | Joseph Effy | Enablement & launch readiness |  | Onboarding Guidance Scope Customer Reqs VDR Plan | Agent/MCP Workflows | Validate onboarding and demos | Publish EA guidance and partner blueprints | Validate GA guides | Run partner and demo rehearsals | Finalize known issues and Day 0 bundle | Publish launch materials and support partners
| Joseph Effy | Evidence, compliance & model trust |  | Benchmark Matrix | Run baselines and repository review | File compliance and validate artifact retrieval | Complete benchmark and EA clearance | Complete security, provenance, and XAI validation | Audit packages and resolve benchmark gaps | Close compliance and approve reports | Approve distribution and publish evidence

## RFM & NIM Launch Tracker
TLD - Need to migrate this to the SDM repo. One or two weeks to complete this code
Matthis needs to review the client SDK --
Need to check guarrails if using Pquery with a non RFM model
Check if we can bring your own custom train table
Ramona to sync with Adi and Manush on ML Flow weights loader and snowflake equiavlent + snowflake
We will copy code and remove dependency (Kumo-API) for SDM
Put deperecated on old GiytHub and PyPI paclages in Kumo
Promote internally
Activity |  |  |  |  | Kumo Contact | External Contact | ETA | Status |  | Pre-requiites |  | Notes
Engineering Readiness
Model
|  | Model - packaged as NIM engieering complete ex. OSRB & QA fixes |  |  | Alex P |  | 2026-07-17 | Complete
|  | Model - NIM meeting OSRB Vulnerability and Dependency requirements |  |  | Alex P |  | 2026-07-31 | On Track |  | Ask Alex+Matthias: When can we have a NIM that includes SDM repo instead of Kumo ML so we can re scan as part of OSRB
|  | Model - QA Validated |  |  | Alex P | John Liu | 2026-07-31 | Complete
|  | Model Weights - Prepared for Hugging Face |  |  | Josh P / Matthias |  | 2026-07-31 | On Track
|  | Model Weights and Inference Source Code and Model Loader - Prepared for GitHub (including readme) |  |  | Josh P / Matthias ? Ramona
SDK
|  | SDK - for RFM NIM only engineering complete ex. OSRB & QA fixes |  |  | Manush |  | 2026-07-17 | Complete
|  | SDK - Package via Kitmaker |  |  | Manush |  |  | Complete |  | Kitmaker, requires OSRB first? |  | Kitmaker already setup. Just waiting OSRB
|  | SDK - addrssing all OSRB Vulnerability and Dependency requirements |  |  | Manush |  |  | Complete |  |  |  | SDM SDK needs to be fully separate of Kump 3.0 and any shared dependency
|  | SDK - Internal QA |  |  | Effy+Ruthvika |  | 2026-07-31 | Complete |  |  |  | Keep the TabICL functionality within the SDM SDK
|  | SDK - QA Validated |  |  | Manush | John Liu | 2026-08-15 | On Track |  |  |  | SDK does not have gradient scores feature
.evaluate should not be supported
| Git Hub Repo |  |  |  | Ramona / | Code Complete | 2026-08-07
Build playground
|  | Build - Playground engineering complete |  |  | Manush |  |  | On Track |  | draft complete. Needs decisions on explainability |  | Josh to follow up on explainability - need to precan
|  | Build - Model card complete | [5 empty] | On Track
|  | Build - QA Validated | [5 empty] | On Track
Publishing
Model
Source code / weights
|  |  | Hugging Face - Publish RFM Weights |  | Ramona? / Manush |  | 2026-08-15 | On Track |  | OSRB of NIM
|  |  | GitHub - Inference Source Code - Weights Loader (stretch) |  | Alex P |  | 2026-08-15 | On Track |  | OSRB of NIM
|  |  | PyPy - Model as a pip wheel / conda package - this is the same as the repo above |  | Ramona? / Manush |  | 2026-08-15 | On Track | Deprioritized |  |  | Initiative to come togerher with SDM repo - meeting with Ramona
|  |  | Databricks - RFM packaged in MLFlow served via Marketplace |  | Adi | Maria Pere-Perez | 2026-08-26 | On Track |  | OSRB of SDK, NVIDIA legal review of "Data Partner Agreement" + signature, Databricks approval of our technical integration
|  |  | Snowflake - RFM packaged as CustomModel in Snowflake Model Registry |  | Manush |  | 2026-08-26 | On Track | Deprioritized | POC done, same as Databricks |  | Snowflake is currently interested in Kumo 3.0 currently so all talks about RFM have been minimized
Container
|  |  | Nvidia NGC - Downloadable NIM container publicly available |  | Alex P |  | 2026-08-15 | On Track |  | OSRB of NIM |  | NVIDIA GPU Cloud (NGC) |  | https://ngc.nvidia.com/signin
|  |  | Docker Hub - Downloadable NIM container publicly available via nvcr.io |  | Alex P |  | 2026-08-15 | On Track |  |  |  | docker login nvcr.io ¦ Example: https://build.nvidia.com/nvidia/nvidia-cuopt/deploy
Free Endpoint / Playground
|  |  | build.nvidia.com - Downloadable NIM container publicly available |  | Same as docker hub |  | N/A | Addressed |  | This is via docker hub
|  |  | build.nvidia.com - Free endpoint live |  | Alex P / Manush | Kris Bhethanabotla. | 2026-08-15 | On Track |  | OSRB of NIM |  | https://nvidia.atlassian.net/wiki/spaces/PYTHON/pages/2564751559/Package+Repositories+PyPI+and+Artifactory
|  |  | build.nvidia.com - Playground live (v1 only) |  | Manush | Kris Bhethanabotla. | 2026-08-15 | On Track |  | OSRB of NIM
SDK
|  | Nvidia PyPy / Conda Repo - Internal |  |  | Manush |  | 2026-08-15 | Complete |  | Kitmaker / OSRB |  | https://nvidia.atlassian.net/wiki/spaces/PYTHON/pages/2564751559/Package+Repositories+PyPI+and+Artifactory | [5 empty] | https://urm.nvidia.com/ui/repos/tree/General/nv-shared-pypi
|  | PyPy Public - Publish SDK to public PyPy as verified under official NVIDIA org |  |  | Manush |  | 2026-08-24 | On Track |  | Kitmaker / OSRB |  | Example: https://pypi.org/project/langchain-nvidia-ai-endpoints/
|  | Andaconda - Publish SDK to Anaconda as Verified Nvidia |  |  | Manush |  | 2026-08-24 | On Track |  | Kitmaker / OSRB |  | https://anaconda.org/search?q=nvidia
Documentation
Model
|  | Supported Hardware Platform(s) - docs |  |  | Effy |  | 2026-07-22 | Complete |  |  |  | See for reference at bottom: https://build.nvidia.com/nvidia/nvidia-cuopt/modelcard
|  | Supported Operating System(s) - docs |  |  | Effy |  | 2026-07-22 | Complete
|  | Raw API Spec |  |  | Effy |  | 2026-07-27 | Complete |  |  |  | https://gitlab-master.nvidia.com/api-catalog/nim-structured-data/-/blob/main/nvidia/kumo-rfm/ux/openapi.yaml
SDK
|  | Supported kernal (python version and kernel dependencies) - docs |  |  | Effy |  | 2026-07-22 | Complete |  |  |  | Get rid of dot please
Usage Guide & Demo notebooks
|  | SDK / Model usage guide (v1 only) |  |  | Effy | Ashwin | 2026-07-31 | On Track |  | need to figure out how to publish internally before GA |  | https://github.com/kumo-ai/docs/tree/effyf/restructure-product-docs
|  | Demo notebook (select one only) updated to new SDK and "Nvidierized" |  |  | Effy |  | 2026-07-24 | Complete
OSRB / NSpect
Model
|  | NIM OSRB Tracker (applicable for NIM container, Weights) |  |  | Alex P / Aleksandar |  | 2026-07-31 | On Track |  |  |  | Ticket | https://nvbugspro.nvidia.com/bug/6457167 |  |  | Tracker: | https://nvidia.atlassian.net/wiki/spaces/NLLMS/pages/3649386904/Kumo-RFM+NIM+Downloadable+NIM+Compliance+Status | Need to tripple check weights and GitHub covered by same OSRB as NIM
|  | GitHub repo |  |  | Ramona? |  |  | Can Catch Up |  | code complete Aug 2nd |  | Ticket: | Need to file
SDK
|  | SDK OSRB (required for PyPi) |  |  | Effy |  | 2026-08-07 | Complete |  |  |  | Ticket: | https://nvbugspro.nvidia.com/bug/6470036 |  | SDK needs separate OSRB. Simpler via KitMaker
Demo Notebooks
|  | Demo Notebooks (OSRB) |  |  | Effy |  | 2026-08-07 | Complete |  | added to SDK ticket |  | Ticket: | https://nvbugspro.nvidia.com/bug/6470036?commentNumber=3
AI Transparency Card
|  | Model Card |  |  | Effy | Ashwin | 2026-07-27 | On Track |  | need to update NGC url |  | https://nspect.nvidia.com/actions/compliance/ai-card/3129/request |  |  | cards need seperate nspect
|  | Container Card |  |  | Effy | Ashwin | 2026-07-24 | Complete |  |  |  | same as above
Branding / Marketing
Branding
|  | Kumo Brand Name - Proposals ready |  |  | Josh | Nicola Sessions | 2026-08-05 | Can Catch Up |  |  |  | Brand and logo required to finalize build
|  | Kumo Brand Logo |  |  | Josh | Nicola Sessions | 2026-08-05 | Can Catch Up
|  | Kumo Brand Name approved by legal / Trademarking |  |  | Josh | Nicola Sessions | 2026-08-05 | Can Catch Up |  |  |  | Requires approx 5 dats need to start Asap
|  | Kumo Brand Name approved by Jenson |  |  | Josh | Nicola Sessions | 2026-08-05 | On Track
Marketing
|  | Blog post / announcement |  |  | Josh | Nicola Sessions | 2026-08-05 | Can Catch Up
|  | GTC Berline Story & approvals (with AIQ) |  |  | Josh / William | Nicola Sessions |  | On Track
AIQ
Engineering
|  | Kumo SDK & Text 2 Pql Integrated into GSF |  |  | Manush |  |  | Complete
|  | Agent Integration proposals for AIQ + GSF integration and GSF only integrations |  |  | Josh |  |  | Complete |  | Ongoing discussions re AIQ/GSF handoffs but our work is largely complete and moving to advisory only
|  | Security integration proposals for AIQ + GSF integration |  |  | Josh |  |  | Complete |  | GSF has gaps to complete
|  | AIQ + Datascience agent scoping for v1 and vision for v2 |  |  | Josh |  |  | On Track |  | Need some additional alignment with GSF
Marketing
|  | Joing AIQ + Kumo ISV / SI deck |  |  | Josh / William |  |  | On Track |  | Need to make updates for Cloudera discussion
Working Docs:
|  | AIQ - Prediction Engineering (official working doc) - Josh section slide 17 onwars |  | https://docs.google.com/presentation/d/1OxETjL72qXIDtd-Fn_3Wn867KZE56fy3CgL7fNUlWK8/edit?usp=sharing
|  | AIQ + Prediction ISV Brief deck (draft only) |  | https://docs.google.com/presentation/d/1vtXLA0T00eXqYESz7jgtMdILYV1nAOeue18UVh-H8KQ/edit?usp=sharing
|  | AIQ + Kumo Berline Demo Story (see slide 20 and 21) |  | https://docs.google.com/presentation/d/1vtXLA0T00eXqYESz7jgtMdILYV1nAOeue18UVh-H8KQ/edit?usp=sharing
|  | AIQ + Kumo Kick off discussion dock |  | NVIDIA_KUMO_AIQ_Intro_Jun10.pptx
|  | Official Tracker for NIM / Model OSRB |  | https://nvidia.atlassian.net/wiki/spaces/NLLMS/pages/3649386904/Kumo-RFM+NIM+Downloadable+NIM+Compliance+Status
|  | Ticket for NIM / Model OSRB |  | https://nvbugspro.nvidia.com/bug/6457167
|  | Ticket for RFM SDK OSRB |  | https://nvbugspro.nvidia.com/bug/6470036
|  | Ticket for Demo Notebook OSRB |  | https://nvbugspro.nvidia.com/bug/6470036?commentNumber=3
Other References
|  | Enterprise AI Factory Deck Offical Marketing Deck |  | https://nvidia.sharepoint.com/:p:/r/sites/EGXProductMarketingTeamSite/Shared%20Documents/GPU%20Genius%20Content/Customer%20Decks/NVIDIA%20Enterprise%20AI%20Factory%20Customer%20Deck.pptx?d=w5c6e4c77cfe8475eadd8974d93437553&csf=1&web=1&e=yFGDbc
|  | cuOpt official docs (as reference) |  | https://docs.nvidia.com/cuopt/user-guide/latest/introduction.html
|  | cuOpt Build Model card (as reference) |  | https://build.nvidia.com/nvidia/nvidia-cuopt/deploy
|  | cuOpt Official Marketing Stategy (as reference) |  | https://docs.google.com/presentation/d/1oenrxye72whSu3c1NLkjAlo9ma4fV8SZ/edit?usp=sharing&ouid=102485869400087361010&rtpof=true&sd=true

## Relational Model Launches
PIC: Matthias; Team:
Release KumoRFM-2 [ available in-house: Aug 1​; available publicly: Sept 15​ Open weights via Hugging Face​ SDK via GitHub​ NIM Factory for Structured Data​ Blueprint​ AI-Q Skill/MCP (GSF, Text2PQL)
Phase/Milestone | Task | Workstream | Assignee | External Dependency | Target Date | Status | Details | Notes | Links
Release StructuredFM(?) model zoo on GitHub
This is an open-source repo to host/release a variety of foundation models for structured data; We are starting with TabICLv2 and KumoRFM-2. Then we also have a place to host our own TFM!
| Base |  |  |  | July 3rd
| Cudf-based data processing |  |  |  |  | done
| Common pre-/post-processing building blocks |  |  |  |  | done
| Common attention modules |  |  |  |  | done
| Out-of-Memory Optimizations (Chunking, etc) |  |  |  |  | done
| Integrate TabICLv2 |  |  |  | July 10th
| Integrate RowEmbedding/ICLBlock |  |  |  |  | done
| Integrate Key/Value Cache |  |  |  |  | done
| Integrate ensembling |  |  |  |  | done
Fp4/fp8 - Integrate on latest hardware
| Ensure parity to TabICLv2 |  |  |  |  | done
| Integrate KumoRFM-2 |  |  |  | July 17th
| Migrate Classification/Regression model |  |  |  |  | done
| Migrate encoders and GNN pipeline |  |  |  |  | done
| Upload model weights to HuggingFace |  |  |  |  | done
| Improve robustness on large-scale subgraphs |  |  |  |  | done
| Explainability for RFM-2 |  |  |  |  | WIP
| Benchmarking |  | ML/Abdullah |  | July 31th
Publish results on RelBench leaderboard
| Move benchmark scripts for reproducibility of published results |  |  |  |  | WIP
| Experience |  |  |  | July 31th
| Provide common interface (in-memory only) |  | Alex |  |  | Done
| Provide current SDK-based FeatureStore/GraphStore, swap out later |  | Alex |  |  | Done
| Provide Skill |  |  |  |  | Done
Provide BYOD examples
Others
| Add nullable support for common data types |  |  |  |  | WIP
| Batch ensembling API |  |  |  |  | WIP
| Text Integration |  |  |  |  | WIP
CODE COMPLETE: 8/1
Hugging Face Release (covered in previous)
TESTING DONE (8/15) | OSRB process for Github code (row 7)
LAUNCH READINESS | Marketing
LAUNCH DATE (9/15)
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Said Aram and @Josh Przybylkocan we fill rows as much as we know today and all the External Dependency names who are people Josh has met.

## Tabular Model Launches
PIC: Matthias; Team:
Release Tabular Foundation Model, including NIM, Blueprints, Benchmarks, HF+GitHub​;available in-house: Sep 1​; available publicly: Oct 15​
Phase/Milestone | Task | Workstream | Assignee | External Dependency | Target Date | Status | Details | Notes
Training
| Classification base model | Training | Valter/Jingang |  |  | In Progress
| Regression base model | Training | Valter/Fede |  |  | In Progress
| Training on longer context sizes | Training | Vedaant |  |  | In Progress
| Scaling Up + multi-node training | Training | Vedaant |  |  | In Progress
Data Generation
| Missing Values | Data Generation | Valter |  |  | In Progress
| Group Prior | Data Generation | Fede |  |  | In Progress
| OOD/Extrapolation/High Frequency | Data Generation | Cedric |  |  | In Progress
Efficiency
| Model Compilation | Efficiency | Matthias |  |  | Complete
Test Time
| Text integration | Test Time | Martin |  |  | Complete | Part of Open Model Repo
| Ensembling | Test Time | Matthias |  |  | Complete | Part of Open Model Repo
| Pre-/post-processing | Test Time | Matthias |  |  | Complete | Part of Open Model Repo
Benchmarking
| TabArena Benchmark | Benchmarking | Valter |  |  | In Progress
| Other Benchmarks (TALENT, Syn. Many-Class, TabStAR, Strable) | Benchmarking | Cedric |  |  | In Progress
| Gilberto Benchmark Integration | Benchmarking | Giba |  |  | In Progress
| Forecasting Benchmarks | Benchmarking | Cedric |  |  | In Progress
| Model Ablations | Benchmarking | Valter |  |  | In Progress
Experience
| Interface/SDK | Experience | Matthias |  |  | Complete
| Blueprints + Examples | Experience
| Upload model/weights to HuggingFace | Experience
| Upload data generation pipeline to GitHub | Experience
| Upload model training/inference pipeline to GitHub | Experience
CODE COMPLETE: 9/1 | Upload Benchmarking Code/Integrate to TabArena | Experience
TESTING DONE (9/15)
LAUNCH (10/15)

## Enablement assets Tracker
Asset | ETA | Urgency | Link | Notes
General Kumo Overview Deck
FSI Kumo Overview Deck | 2026-10-16
Kumo Engine Demo notebook
SDM Library Demo notebook | 2026-10-20 | P0 |  | Tubi presentation

## PM Initiatives Tracker
Activity
Cloudera | Attendees: Vanja, Patrick (from Cloudera)
Need to help Joe with Fraud Blue Print One-Two pages
Update Fraud Pitch deck with Joe + Disha + Me
Prep for Dell team
Kick off work to add support for SDM standard for nvTesseract models
Get articles and research from Kumo.ai and place in new docs | Work with Alexander and Leena
Create timeline and details tracker for NIM 2 launch, incudes Tabular foundation model | In progress
Get input from Alexandria and Negar on how they deal with small PRs post OSRBs
Update Oct 18th to EA Enterprise Licence
Write script for formal Snowflake Live demo with Haowei
Get linear
2.5

## (OLD) KumoV3 launch (hidden)
July 15 milestones here: https://docs.google.com/document/d/1XCKhuo6lsbWHkj9MDFQICL6GrpfpkL5hUnxXGG_zgho/edit?tab=t.eii1633ozjq0
Any partner or internal team may build the all of the containers from source (github) to run kumo locally
Prebuilt containers also available at an internal staging location
Task | PIC | Timeline | Status | Contributors | Description | Ticket as applicable
Support On-Prem Install | Daniel | DGX Spark by Jul 24 | Done |  | Be installable by NVIDIA customers like NPCI
SaaS Staging Envs | Joseph | 2026-07-31 | Done | Isaac, Ruthvika, Devan, Angela | Tubi, Expedia, Discord, Reddit, Yieldmo, Doordash, Sothebys
Customer Comms Start | Disha | 2026-08-01 | Done |  | Finalize messaging for all customers
OSRB Done | Joseph | 2026-08-07 | Done | Grayson, Elvin | Unblocking Stantander, Coinbase, Affirm, P&G, etc | https://nvbugspro.nvidia.com/bug/6441538
Customer Comms Done | Disha | 2026-08-31 |  |  | All customers have agreed to transition plans
Support Pip Install | Elvin | 2026-07-24 |  | Haowei | Code Complete & Tested
Support Databricks Notebook | Elvin | 2026-08-31 |  |  | Code Complete & Tested
Support Snowflake Notebook | Haowei | 2026-08-31 |  |  | Code Complete & Tested
Santander Installed | Joseph | 2026-08-31
DD + Wolt + Deliveroo | TBD | TBD
Tubi on Kumo 3 | TBD | TBD
Coinbase on Kumo 3 | TBD | TBD
Affirm on Kumo 3 | TBD | TBD
Discord on Kumo 3 | TBD | TBD
Reddit on Kumo 3 | TBD | TBD
Sotheby's on Kumo 3 | TBD | TBD
Yieldmo on Kumo 3 | TBD | TBD
Expedia on Kumo 3 | TBD | TBD
Source Code Published on GH | Joseph | 2026-09-15 |  |  | Has dep on marketing + legal
Communicate to open source customers | Disha | 2026-09-15
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Zack Drach @Joseph Oliveira When was OSRB submitted and can you link ticket

## (OLD) High Level Tracker (hidden)
|  | Marketing |  | 2026-09-28 |  | Candidate for GTC Berline
|  |  | Code Complete EST | GA Date | Status Aug 6th | Key updates | Key risks / notes | nspect link
Nemotron Structured RFM
| NIM RFM v1 (Nemotron V1 uses KumoRFM v2) |  |  | 2026-08-24 | At Risk | OSRB for NIM and SDK complete. Build page complete | TabICL was not disclosed on OSRB (ticket updated). Last minute changes requested on SDK which may retrigger scans and QA. Discuss change to EA licence | model nspect https://nspect.nvidia.com/review?id=NSPECT-B1D1-PT0E
container nspect https://nspect.nvidia.com/review?id=NSPECT-ZP0R-U13D
| NIM RFM v2 (SDM base) |  |  | 2026-09-28 | Can Catch Up | This is the same model as v1 just ported to SDM. Awaiting SDM code complete. Expect quick OSRB turn around | Need to add explainability | need to register a new version under the programs above
[6 empty] | hugging face weights goes public with this version | https://nvbugspro.nvidia.com/bug/6575672
| RFM v2.5 (No Tab ICL) |  |  | 2026-01-15 | On Track | ?? Need update
Nemotron TFM
| TFM v1 ¦ (NIM, hugging face, Repo with training, Build) |  | September 1st | 2026-09-28 |  | Training recipe and generators | Need to ok with Jure. Will need benchmarks and paper
[7 empty] | update and reuse this nspect | https://nspect.nvidia.com/review?id=NSPECT-I0E0-OIXC
OSRB / Nspect Tickets
|  | Build playground launch |  |  |  | Effy to update build team on timeline and share example for playground
Nemo Structured "Kumo" Training/Inference
| Kumo 3.0 - pre release version |  |  | 2026-08-15 | Can Catch Up | OSRB for code and SDK complete | This is the container version pre "Kumo core", for delivery to Santandeer. Discussion re restarting OSRB and jumping straight to 3.1 (pip installable version) | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2
| Kumo 3.1 - pip |  |  | 2026-09-30 | On Track | Agreed would cut EA Nspect ticket only for Snow/DBx release only | nspect is a new EA version under kumo3 | https://nspect.nvidia.com/registration/programs/22455/versions/76584
SDM
| SDM v1 | https://github.com/NVIDIA/structured-data-models/ | Aug 20th (for explainability) | 2026-09-28 |  | Code complete expected Aug 7. Expect 1 month for OSRB. Key input to NIM v2 | nspect | https://nspect.nvidia.com/review?id=NSPECT-MAR9-ANXN
[7 empty] | osrb ticket | https://nvbugspro.nvidia.com/bug/6630830
Databricks |  |  | < check dates from earlier standup; later
RFM on DBx
|  | NIM RFM v2 Marketplace Listing (model weights) |  | 2026-09-28 | Can Catch Up | PoC complete. Need new new supplemental Data Sharing Agreement. In process
RFM v1 via pip install in Notebook (via SDM)
SDK Optimizations (SM, auth, sampling)
|  | Genie Text-2-pql skills |  | 2026-09-28 | Stretch
Kumo 3.1 - pip on Snowflake
NSpect ticket for Snowflake EA
Snowflake
RFM on Snowflake
|  | RFM v1 via SPCS only (no app) |  | 2026-09-28
RFM via pip install in Notebook
SDK Optimizations (SM, auth, sampling)
|  | Cortex Text-2-pql skills |  | 2026-09-28 | Stretch
| Kumo 3.1 - pip on Snowflake |  | < higher priority for Snow
NSpect ticket for Snowflake EA
Branding | Website
Library naming
Naming options confirmed with marketing
Naming options confirmed with JJH
| Draft Script for GTC Berlin | Columns:
Draft
| Website | testing complete
... osrb... nspect... get from JP, AP, JO . Create subtasks with PICs and dates.. etc
Website Ideation
Website final design
| Blog(s) for launch |  | Capture ticket numbers, etc. |  |  | 3.0 & 3.1 line items> Zack and Joseph
Zack and Matthias first to fill as much
Matthias > TFM, RFM (code complete dates)... Effy and AP for dates after that
0. Update RFM NIM v1 OSRB ticket to discuss TabICL dependency
1. start OSRB for SDM repo
2. start NSpect ticket for Snowflake EA special Kumo 3.0 pip install build with Howai -- poke Howei to make sure he is ready
3. Check in with Alex has she started NIM v2 for RFM (using the SDM base)
4. Check in with Alex & Matthias will RFM NIM v2 get rid of TabICL depency if not when will we have an RFM with no dependency (when is RFM 2.5??? -- cos this was meant to be NIM v2. Will this be a NIM v3 and when can we start the OSRB?)
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 21-Aug: Kumo 2 Customers Reply: 15-Aug: Internal Nvidia SA's

## OLD - NIM Containerization (hidden)
PIC: Alex. Team: Alex, Manush, Matthias, Josh, Said
Core Infra needed for both the following Top 5: (a) Release KumoRFM-2 [ available in-house: Aug 1​; available publicly: Sept 15​ (b) Release Tabular Foundation Model ​; available in-house: Sep 1​; available publicly: Oct 15​
Phase/Milestone | Task | Workstream | Assignee | External Dependency (person/team) | Target Date | Status | Details | Notes | Links
Development | Finalize API design | NIM container implementation | Alex Porter |  | 6/8 | Complete | Kumo RFM+TabICL API Proposal | first step in the full NVIDIA API process | API Docs
| PRD | UX/documentation | Alex Porter, Said Aram |  | 6/12 | Complete | Need formal PRD for QA team (and in general but that's the first we've been asked) | Need Josh help on the PRD. If Josh is too packed before DTO, Said take over.
| Pilot/POC NIM container for TabICL | NIM container implementation | Manush Murali US |  | 6/16 | Complete | No standardized scaffolding, just working docker container | Unoptimized Version | Gitlab Container
| Pilot/POC RFM NIM container | NIM container implementation | Alex Porter |  | 6/16 | Complete | No standardized scaffolding, just working docker container
| Optimize RFM implementation | NIM container implementation | Alex Porter |  | 7/7 | Not Started
| solidify API spec in Gitlab + pass validation pipelines | Distribution pathway | Alex Porter |  | 6/26 | Complete
| Support in nim_builder and nimtools | NIM container implementation | Alex Porter |  | 7/2 | Complete | Submit changes for NIM type to actual nim_builder/nimtools code repos
| Integrate tfm-serving to RFM | NIM container implementation | Alex Porter |  | 6/18 | Complete
| Shared runtime (tfm-serving) for TFM NIMs | NIM container implementation | Manush Murali US |  | 7/2 | Complete | Pydantic models, shared validation logic, Arrow decoding, response formatting. Model-specific adapters |  | Gitlab Package
| Container build system | NIM container implementation | Alex Porter |  | 7/2 | Complete | Category-specific build system for shared container + model-specific adapter logic
| Optimized TabICL implementation (not a deliverable only for learning) | NIM container implementation | Manush Murali US |  | 7/2 | Complete | Followup improves to tabICL - will start the release/QA process on the early init version but then update with this | TabICL Optimization Report | Gitlab Repository
| TabICL/Single table SDK | UX/documentation | Manush Murali US |  | 7/10
| RFM SDK | UX/documentation | Alan Krumholz, Isaac Gutierrez |  | 7/10 | Complete | kumoai[rfm-nim] version of kumo-sdk and a tabICL demo client | Same as current Kumo SDK spec.Furure versions will include Database connectors. Need Alex+Matthias discussion
| Benchmarking: model performance | Benchmarking | Alex Porter |  | 7/24 | In Progress | initial benchmarking for QA done; todo is reproducing rfm paper
| Benchmarking: throughput, latency, GPU SKU capacity | Benchmarking | Ruthvika Kosuri |  | 7/10 | Complete |  | https://docs.google.com/spreadsheets/d/1qCkAP6ndJ9f_3oUolVkUbLteP_POpkl5YneHCok2jZY/edit?gid=1288133001#gid=1288133001
| Baseline TabICL Deployment | Benchmarking | Ruthvika Kosuri |  |  |  | Deferred for now
CODE COMPLETE: 7/10
INTERNAL LAUNCH READINESS | NGC org for containers | Distribution pathway | Alex Porter |  |  | Complete | using nvstaging for now but we also own "Structured Data & Graph Models" with teams for nims and kumo3
| Submit API for onboarding/approval | Distribution pathway |  |  |  |  | https://gitlab-master.nvidia.com/api-standards/api-registry/pipeline/publication#onboarding | Will have Text2PQL. Will resemble current playground
| request to publish on inference.nvidia.com | Distribution pathway | Said Aram | Deep Debroy | 7/1 | Complete | submit https://inference.nvidia.com/model-requests with justification; then get Manush and Disha to have other stakeholders upvote it
| Submit requested SKU, benchmarking perf etc for NIMs to inference.nvidia.com | Distribution pathway | Alex Porter, Said Aram |  | 7/8 | Complete
| submit NIM container to inference team | Distribution pathway | Alex |  | 7/17 | In Progress
TESTING DONE (7/24). Build.NVIDIA.com (internal release)
EXTERNAL LAUNCH READINESS | Build web app - frontend - TabICL/single table UX | build.nvidia release |  |  |  |  | Deferred for now
| Build web app - frontend for RFM (multitable) | build.nvidia release | Effy Fang, Manush
| Build backend (connect to NIM?) | build.nvidia release | Alex |  |  | Not Started
| Hugging face RFM weights | Distribution pathway | Josh P |  | 2026-07-07
| OSRB process |  | Josh P |  |  |  |  | A lot of this overlaps what Kirill is doing in the NIMs track
| SWQA Go launch | Distribution pathway | Alex Porter | John Liu |  | Complete |  | contact = John Liu
| Share initial containers with Compliance | Distribution pathway | Alex Porter | Kirill Buryak |  | Complete | https://nvaiinfa.aha.io/epics/PMS-E-2371?active_tab=related
| Put actual NSpect IDs on Aha | Distribution pathway | Alex Porter | Kirill Buryak |  | Complete
| Marketing Language for build.nvidia.com |  |  |  | 2026-07-07 |  | Key is do not have dependencies on other open source with bad licenses eg., BSD, no CVEs etc etc
LAUNCH DATE (9/15)
Josh Notes
Isaac and Ruthvica (Allen as Manager) working on RFM only SDK. Need to also determine licence? | <- No process yet on how to release.
For Build playground - will hard code PQL options -- adding SDK to complex for V1. Likely will do so as follow up V2 |  | Meeting happening Friday. Isaac may be person we insert. Need to talk with Isaac with some oversight (Effy --> Make Effy Point of Contact)
Kumo-tabular-launch-models (design review tomorrow)
Look at palming off OSRM to Effy as well
Currently purely RFM NIM --> Single table NIM may come in soon (need to check with Matthias)
Build endpoint teams release cycle - they have 8/13 canary deployment, 8/18 production live deploy. Everything works back from there
As soon as we have QA go -- we can
Two Tracks: Build Endpoint (Nvidia hosted demo UI); NGC actually downloadable NIM; Hugging face - two .pt files … just the weights not the NIM; Also Training data generators and code on Github
Right now NIM is packaged with Weights; In theory we can make NIM without the weights and the weigjts can be pulled live from NGC or Hugging face (applicable to frewquent weight updates) Our NIM will pull the same weigjts fron NGC not Hugging Face
Some NIM pull weights from Hugging Face
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Said Aram, @Josh Przybylko and @Alex Porter we need to fill these parts out over the next days. Reply: @Alex Porter and @Matthias Fey you need some work here to make a path for HF models to make their way to NIM and sequence that.

## OLD - July 2nd Deliverables (hidden)
Task | Workstream | Assignee | External Dependency (person/team) | Target Date | Status | Details | Notes | Links
| Demo for Jensen |  |  | 2026-07-01
Slide with Tab Arena Benchmark
Slide with Min's tradeoff on GTM
Slide with Disha's use case discovery

## LAUNCH MATRIX (OLD) (hidden)
LAUNCH MATRIX
RELEASE |  |  | CODE FREEZE COMPLETE |  | QA TESTING COMPLETE |  | EA (IF APPLICABLE) |  | GA |  | STATUS |  | TICKETS & CUSTOMERS
Program | Release | PIC | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Status | Notes — why it is at risk / what is happening | OSRB Ticket | NSpect Ticket | Other Tickets / Links | EA Customers
Nemotron RFM Model | KumoRFM-2 model + open repo (SDM V1) | Matthias (Alex, Abdullah) | 2026-08-01 | 2026-08-07 | NA | NA | 2026-08-01 |  | 2026-09-15 |  | Can Catch Up | The underlying model release: open weights on Hugging Face, SDK on GitHub, model zoo repo. Base work is done — cuDF processing, TabICLv2 integration, KumoRFM-2 migration and the Hugging Face weight upload all landed. Still open: explainability, RelArena benchmarking. OSRB on the GitHub code has still not been filed, which gates the public release. Blocker: We want to integrate Nemotron Tabular there, and I assume we want to announce this together? How shall we do this? The repo is done, but we would need to have a second fast-follow up release with Nemotron Tabular. | https://nvbugspro.nvidia.com/bug/6630830 | https://nspect.nvidia.com/review?id=NSPECT-MAR9-ANXN | Repo: github.com/NVIDIA/structured-data-models
Nemotron RFM NIM | NIM RFM v1 | Alex / Matthias | 2026-07-17 | 2026-07-17 | 2026-07-15 | 2026-07-12 |  |  | 2026-08-24 |  | At Risk | Only blocker is final naming - legal approval is complete including all nspect and osrb tasks | https://nvbugspro.nvidia.com/bug/6457167 | https://nspect.nvidia.com/review?id=NSPECT-B1D1-PT0E | 4 more — SDK/notebook OSRB nvbug 6470036, container NSPECT-ZP0R-U13D, AI card 3129, compliance tracker. See Tickets tab.
Nemotron Client | SDK for Structured Model NIMS | Manush | 2026-08-11 | 2026-08-11 | NA | NA | 2026-08-18 |  | 2026-08-24 |  | At Risk | Only blocker is final naming - legal approval is complete including all nspect and osrb tasks. Needed for AIQ, Snowflake, & Databricks RFM integration | https://nvbugspro.nvidia.com/bug/6470036 | https://nspect.nvidia.com/review?id=NSPECT-USU5-DBYK | Repo: github.com/NVIDIA/nemotron-structured-client
Nemotron RFM Model | NIM RFM v2 (SDM base) | Alex | [6 empty] | 2026-09-28 |  | At Risk | Cannot start until SDM v1 is code complete — this is a straight port of v1 onto SDM, so the schedule is entirely inherited. Explainability still has to be added. Hugging Face weights go public with this version. OSRB should be quick once the code lands. | https://nvbugspro.nvidia.com/bug/6575672 | New version still to be registered under the RFM programs
Nemotron RFM Model | RFM v2.5 (no TabICL) | Matthias | 2026-12-01 | [5 empty] | 2027-01-15 |  | On Track
Nemotron RFM NIM | NIM RFM v2.5 (no TabICL) | Matthias | [6 empty] | 2027-01-15 |  | On Track
Nemotron TFM Model | TFM v1 | Matthias / Jingang | 2026-09-01 | 2026-09-08 | 2026-09-15 |  | 2026-09-01 |  | 2026-10-15 |  | On Track | Currently training a scaled-up version which will finish in about a week. But we encounter training instabiltiy issue at the moment. We're doing our best to solve it. We've located the problem, but we need to come up with a good solution. The current checkpoints we have are quite good, but not yet #1. Final integration into SDM has started + Benchmarking work. This will land early September, but probably with a few days of delay wrt initial timeline. |  | https://nspect.nvidia.com/review?id=NSPECT-I0E0-OIXC | Reuse the existing NSpect rather than filing new
Nemotron TFM NIM | NIM TFM v1 | Matthias / Jingang | [6 empty] | 2026-10-15 |  | On Track
Kumo 3 | Kumo 3.0 — container | Zack / Joseph / Daniel | 2026-09-30 |  | 2026-10-15 |  | 2026-08-05 | 2026-08-05 | Oct 22 (tentative) |  | Can Catch Up | No formal code complete or testing date was ever set for 3.0 — Zack and Joseph need to supply them. OSRB cleared 7-Aug, which unblocks Santander, Coinbase, Affirm and P&G. On-prem install (DGX Spark) landed 24-Jul and SaaS staging envs 31-Jul. Planned GA of 15-Aug sits before the 31-Aug Santander install, so the sequence needs fixing. Open question: restart OSRB and jump straight to 3.1? | https://nvbugspro.nvidia.com/bug/6441538 (Prev) https://nvbugspro.nvidia.com/bug/6619129 (Current) | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2 |  | Santander, NPCI, P&G, Paypal
Kumo 3 | Kumo 3.1 — pip | Zack / Elvin / Haowei | 2026-09-30 |  | 2026-10-15 |  |  |  | Oct 22 (tentative) |  | On Track | 'Support pip install' was promised 24-Jul as both code complete and tested, but was never marked done — Elvin to confirm whether it actually landed. The EA NSpect ticket was agreed for the Snowflake and Databricks release only, and both dependent tickets are still unfiled. | https://nvbugspro.nvidia.com/bug/6649311 | https://nspect.nvidia.com/registration/programs/22455/versions/76584 | PLR: https://nspect.nvidia.com/actions/compliance/legal/software/1774/request export compliance: https://nvbugspro.nvidia.com/bug/6649367 | snowflake
Kumo 3 | Kumo 3 source on GitHub | Zack / Joseph | 2026-09-30 |  | 2026-10-15 |  |  |  | Oct 22 (tentative) |  | On Track | Waiting on marketing and legal sign-off before the source can be published. Disha communicates to open-source customers on the same date. | https://nvbugspro.nvidia.com/bug/6648800
SDM | KumoRFM huggingface model weights | Ramona | [8 empty] | On Track
SDM | SDM v1 | Ramona | 2026-08-20 | [5 empty] | 2026-09-28 |  | On Track | Duplicate or row 4? | https://nvbugspro.nvidia.com/bug/6630830 | https://nspect.nvidia.com/review?id=NSPECT-MAR9-ANXN | Repo: github.com/NVIDIA/structured-data-models
Databricks | RFM on Databricks | Josh / Adi / Elvin | 2026-08-31 |  |  |  | blocked by row 4 |  | 2026-09-28 |  | Can Catch Up | Legal is the blocker, not engineering: needs a supplemental Data Sharing Agreement plus NVIDIA legal review of the Data Partner Agreement. PoC is complete and the MLFlow Marketplace listing has a publish ETA of 26-Aug (Adi with Maria Pere-Perez). RFM v1 pip-in-notebook is code complete and tested 31-Aug. EA is 'mid-December per Zack' which cannot follow a 28-Sep GA — needs a real date. Genie Text-2-PQL is a stretch goal. |  |  |  | Mid-Dec per Zack — needs a real date
Databricks | Kumo 3.1 on Databricks | Adi / Elvin | 2026-09-30 |  | 2026-10-15 |  | 2026-09-15 |  |  |  | On Track | 'Support Databricks notebook' is due code complete and tested 31-Aug. The NSpect EA ticket has still not been filed, and no GA date has been set. |  | EA NSpect — not yet filed
Snowflake | RFM on Snowflake | Manush / Adi |  |  |  |  | blocked by row 4 |  | 2026-09-28 |  | On Track | Scope is the open question — the standup said 'RFM not needed' for Snowflake, so confirm before more effort goes in. This workstream is higher priority than Databricks. RFM v1 runs via SPCS only, no app. Manush and Adi still owe publishing dates. Cortex Text-2-PQL is a stretch goal.
Snowflake | Kumo 3.1 on Snowflake | Haowei | 2026-09-30 |  | 2026-10-15 |  | 2026-08-21 |  |  |  | On Track | Highest-priority Snowflake item. 'Support Snowflake notebook' is due code complete and tested 31-Aug. The NSpect ticket for the special Kumo 3.1 pip-install EA build has been filed. PLR opened with Kevin |  | EA NSpect https://nspect.nvidia.com/registration/programs/22455/versions/76584 | https://nspect.nvidia.com/actions/compliance/legal/software/1774/request

## Tickets (old) (hidden)
ALL TICKETS
Release | What it covers | System | Ticket / ID | Status | Link
KumoRFM-2 model | OSRB for the GitHub model-zoo code | nvbug | — | NOT FILED
NIM RFM v1 | NIM + model OSRB | nvbug | 6457167 | Reopened — TabICL not disclosed | https://nvbugspro.nvidia.com/bug/6457167
NIM RFM v1 | SDK OSRB (required for PyPI) | nvbug | 6470036 | Filed, in review | https://nvbugspro.nvidia.com/bug/6470036
NIM RFM v1 | Demo notebooks OSRB | nvbug | 6470036 comment 3 | Filed, in review | https://nvbugspro.nvidia.com/bug/6470036?commentNumber=3
NIM RFM v1 | Model NSpect | NSpect | NSPECT-B1D1-PT0E | Registered | https://nspect.nvidia.com/review?id=NSPECT-B1D1-PT0E
NIM RFM v1 | Container NSpect | NSpect | NSPECT-ZP0R-U13D | Registered | https://nspect.nvidia.com/review?id=NSPECT-ZP0R-U13D
NIM RFM v1 | AI transparency card (model + container) | NSpect | AI card 3129 | Requested | https://nspect.nvidia.com/actions/compliance/ai-card/3129/request
NIM RFM v1 | Downloadable NIM compliance tracker | Confluence | NLLMS space | Reference | https://nvidia.atlassian.net/wiki/spaces/NLLMS/pages/3649386904/Kumo-RFM+NIM+Downloadable+NIM+Compliance+Status
NIM RFM v2 | Referenced bug | nvbug | 6575672 | Open | https://nvbugspro.nvidia.com/bug/6575672
NIM RFM v2 | NSpect | NSpect | new version | NOT FILED — register under RFM programs
TFM v1 | NSpect (reuse existing) | NSpect | NSPECT-I0E0-OIXC | Registered | https://nspect.nvidia.com/review?id=NSPECT-I0E0-OIXC
Kumo 3.0 | OSRB | nvbug | 6441538 | Resolved 7-Aug | https://nvbugspro.nvidia.com/bug/6441538
Kumo 3.0 | NSpect | NSpect | NSPECT-1HFF-6ET2 | Registered | https://nspect.nvidia.com/review?id=NSPECT-1HFF-6ET2
Kumo 3.1 | NSpect EA version (kumo3 programme 22455) | NSpect | v76584 | Registered | https://nspect.nvidia.com/registration/programs/22455/versions/76584
Kumo 3.1 on Snowflake | NSpect EA — special Kumo 3.0 pip-install build | NSpect | — | NOT FILED
Kumo 3.1 on Databricks | NSpect EA | NSpect | — | NOT FILED
SDM v1 | Repo OSRB | nvbug | 6630830 | Filed — OSRB not started, allow ~1 month | https://nvbugspro.nvidia.com/bug/6630830
SDM v1 | Source repository | GitHub | structured-data-models | Reference | https://github.com/NVIDIA/structured-data-models/
Build playground + docs | Package repositories — PyPI and Artifactory | Confluence | PYTHON space | Reference | https://nvidia.atlassian.net/wiki/spaces/PYTHON/pages/2564751559/Package+Repositories+PyPI+and+Artifactory